LAB 04

Experiment Problem

Prepare a Software Project Management Plan (SPMP) for the AI Resume Analyzer & Interview Preparation System and estimate the project size, effort, resources, cost, and staffing requirements using appropriate software estimation techniques.

Objective

To prepare a Software Project Management Plan (SPMP) for the AI Resume Analyzer & Interview Preparation System and estimate the project size, development effort, time, resources, cost, and staffing requirements using Basic COCOMO and Putnam–Norden staffing estimation techniques.

Solution

project estimates

1.Historical Data Used

The estimation process is based on observations from previous academic software development projects of similar scale and complexity, particularly web-based application involving resume processing, user authentication, database management, and basic AI/ML-based analysis. Such students-level projects generally involve approximately 4,000-6,000 lines of code (LOC) and are developed within a period of about 10-12 weeks (about 3 months) by a small team. These observations provide a reasonable baseline for estimating the size, effort, resources, and cost of the proposed AI Resume Analyzer & Interview Preparation System.

2. Estimation Techniques Used

The Basic COCOMO (Constructive Cost Model) is used to estimate the development effort, cost, and duration of the project based on the estimated lines of Code (LOC). The system is considered an Organic Project, as it is a relatively small academic project developed by small teams using familiar technologies with moderate complexity.

Fie estimating resource and staffing requirements, the Putnam-Norden Rayleigh Curve Model is considered. It represents the variation in staffing levels throughout the project, with manpower gradually increasing during the development phase and decreasing during testing, documentation, and final deployment.

3.Estimates

- Size estimates

Based on the planned functionality of the AI Resume Analyzer & Interview Preparation System, the estimated project size is approximately 5,000 LOC.

| Module/Component | Approx. Loc |
| --- | --- |
| User Interface / Frontend | 800 – 1,000 |
| Backend and API Handling | 1,200 – 1,500 |
| Resume Upload and Parsing | 600 - 800 |
| Resume Analysis / Skill Extraction | 700 - 900 |
| Interview Preparation Module | 500 - 700 |
| Database, Validation and Testing | 400 - 600 |
| Total Estimated Size | ~5,000 LOC |

The estimated size includes the frontend, backend, database interaction, resume processing, analysis logic, and interview preparation functionality.

- Effort and Time Estimation (COCOMO Basic Model)

For an Organic Project, the Basic COCOMO Model is used:

Effort(E) = 2.4 *(KLOC)^1.05

For the estimated project size:

KLOC = 5,000/1,000 = 5KLOC

Therefore,

E = 2.4*(5) ^1.05 ~13.0 person-months

The estimated development effort is therefore approximately 13 person-months.

The Development duration is estimated using:

Duration = 2.5 * (Effort)^0.38

Thus, the estimated full development duration is approximately 6 – 7 months. Since this is an academic prototype, the actual project schedule will be adjusted according to the academic timeline and available team resources.

- Resource Estimation

Considering the student-level development requirements, the project will require:

Team Composition:

- 1 Project Lead/ System Coordinator

- 2 Developers

- 1 AI/ML & Testing Member

Hardware Resources:

- Personal computers/laptops for development

- Stable internet connection

- Mobile devices for testing the web application

Software Resources:

- Development Environment: VS Code

- Programming Languages: Python, HTML, CSS, JavaScript

- Version Control: Git and GitHub

- Database: MySQL / PostgreSQL

- Backend Framework: python-based framework

- AI/ML Libraries: Python ML/NLP libraries

- Resume Processing: PDF/ document parsing libraries

- Hosting: Free-tier cloud hosting services

4. Cost Estimation

The total Project cost consists of human-resource expenses and operational expenses such as hosting, domain, software tools, internet, and testing resources.

Using the Basic COCOMO model, the estimated effort is approximately 13 person-months. For an academic project, the development team is considered to use existing student resources; therefore, the major operational costs are expected to remain limited.

| Item | Estimated Cost (INR) | Remarks |
| --- | --- | --- |
| Domain purchase (.com/ .in) | ₹1,000 - ₹1,500/year | Optional official web presence |
| Hosting and Cloud services | ₹3,000 - ₹4,000/year | Paid usage after free-tier limits |
| Software / Development Tools | ₹0 - ₹2,000/year | Mostly open source/free tools |
| AI/ML APIs or Services | ₹1,000 - ₹3,000 | Depends on API usage |
| Internet and Testing | ₹2,000 - ₹3,000 | Testing and development connectivity |
| Miscellaneous Expenses | ₹1,000 - ₹2,000 | Documentation and other minor expenses |
| Estimated Operational Cost | ₹8,000 - ₹15,500 | Approximate |

The project primarily uses open-source development tools and student-owned hardware, which significantly reduces the overall development cost.

5.Staffing Level Estimation (Norden’s Work)

According to the Norden staffing model, manpower requirements generally follow a        Rayleigh distribution throughout the project lifecycle.

- Staffing gradually increases during the requirement analysis, design, and implementation phases.

- The maximum staffing level is expected during the development and AI/ML integration phase.

- Staffing gradually decreases during testing, documentation, and deployment.

- During the final stage, approximately 1-2 members may be sufficient for testing, documentation, bug fixing, and deployment.

6.conclusion

After completing this experiment, we learned how to prepare a Software Project Management Plan (SPMP) for a software project. We understood how to estimate project size using Lines of Code (LOC) and calculate development effort and time using the Basic COCOMO model. We also learned how to identify the required hardware, software, human resources, operational costs, and staffing levels using the Putnam–Norden staffing model.