Lab 6

Experiment 01(6.1)

Title

Project scheduling using Activity Network and Gantt chart

Problem statement

A Software project requires the following activities with their durations and immediate predecessors. Construct the Activity Network representation of the project.

Given Data

| Activity No. | Activity Name | Duration (Weeks) | Immediate predecessor |
| --- | --- | --- | --- |
| 1 | Obtain requirements | 4 | - |
| 2 | Analyze operations | 4 | 1 |
| 3 | Define subsystems | 2 | 1 |
| 4 | Develop database | 4 | 1 |
| 5 | Make decision analysis | 3 | 2 |
| 6 | Identify constraints | 2 | 5 |
| 7 | Build module 1 | 8 | 3, 4, 6 |
| 8 | Build module 2 | 12 | 3, 4, 6 |
| 9 | Build module 3 | 18 | 3, 4, 6 |
| 10 | Write report | 10 | 6 |
| 11 | Integration and test | 8 | 7, 8, 9 |
| 12 | Implementation | 2 | 10, 11 |

Objective

To schedule the activities of a software project using an Activity Network and Gantt Chart by considering the duration and dependency of each activity.

Solution

The activities are scheduled according to their predecessor relationships.

The dependency sequence is:

1 → 2 → 5 → 6

After activities 3, 4 and 6 are completed, activities 7, 8 and 9 can start.

Activity 10 starts after activity 6.

Activity 11 starts after activities 7, 8 and 9 are completed.

Activity 12 starts after activities 10 and 11 are completed.

Activity Network

┌────→ 3 ─────┐

│             │

START ───→ 1 ───→ 2 ───→ 5 ───→ 6 ───┼──→ 7 ───┐

│                            │         │

├──────────→ 4 ─────────────┼──→ 8 ───┤

│                            │         │

│                            └──→ 9 ───┤

│                                      ↓

│                                     11

│                                      │

│                                      │

└──────────────────────────────→ 10 ───┤

↓

12

↓

FINISH

Scheduling Calculation

| Activity | Duration | Earliest start | Earliest Finish |
| --- | --- | --- | --- |
| 1 | 4 | 0 | 4 |
| 2 | 4 | 4 | 8 |
| 3 | 2 | 4 | 6 |
| 4 | 4 | 4 | 8 |
| 5 | 3 | 8 | 11 |
| 6 | 2 | 11 | 13 |
| 7 | 8 | 13 | 21 |
| 8 | 12 | 13 | 25 |
| 9 | 18 | 13 | 31 |
| 10 | 10 | 13 | 23 |
| 11 | 8 | 31 | 39 |
| 12 | 2 | 39 | 41 |

Gantt Chart

Time (Weeks) → 0    4    8   12   16   20   24   28   32   36   40 41

Activity 1      ████████████

Activity 2                  ████████████

Activity 3                  ██████

Activity 4                  ████████████

Activity 5                              █████████

Activity 6                                        ██████

Activity 7                                              ████████████████████

Activity 8                                              ██████████████████████████████

Activity 9                                              ███████████████████████████████████████████

Activity 10                                             █████████████████████████

Activity 11                                                                            ████████████████████

Activity 12                                                                                              ██████

Critical Path

The critical path is:

1 → 2 → 5 → 6 → 9 → 11 → 12

Total duration:

4 + 4 + 3 + 2 + 18 + 8 + 2 = 41 weeks

Therefore,

Total Project Duration = 41 weeks

Result

The Activity Network and Gantt Chart for the given software project were successfully constructed. The total project duration is 41 weeks.

Conclusion

Activity Network and Gantt Chart techniques help in planning and scheduling software projects. They show the dependencies, duration and sequence of project activities and help in identifying the critical path.

Experiment-2(6.2)

Title

Project Scheduling using PERT Chart

Problem Statement

Consider a software project with five tasks T1–T5. The durations of the tasks are 3, 2, 3, 5 and 2 weeks respectively. T2 and T4 can start when T1 is complete. T3 can start when T2 is complete. T5 can start when both T3 and T4 are complete. Draw the PERT chart of the project. Find the latest start date of T3, slack time of T4 and the critical path.

Given Data

| Task | Duration (Weeks) | Immediate predecessor |
| --- | --- | --- |
| T1 | 3 | - |
| T2 | 2 | T1 |
| T3 | 3 | T2 |
| T4 | 5 | T1 |
| T5 | 2 | T3, T4 |

Objective

To construct a PERT chart and determine the earliest start, earliest finish, latest start, latest finish, slack time and critical path of a software project.

Solution

The dependency relationships are:

T1 is the starting activity.

T2 and T4 start after T1 is completed.

T3 starts after T2 is completed.

T5 starts only after both T3 and T4 are completed.

PERT Chart

┌──→ T2 (2) ──→ T3 (3) ──┐

│                          │

START ──→ T1 (3) ─┤                          ├──→ T5 (2) ──→ FINISH

│                          │

└──→ T4 (5) ──────────────┘

Forward Pass Calculation

For T1:

ES = 0

EF = ES + Duration = 0 + 3 = 3

For T2:

ES = 3

EF = 3 + 2 = 5

For T4:

ES = 3

EF = 3 + 5 = 8

For T3:

ES = 5

EF = 5 + 3 = 8

For T5, both T3 and T4 must be completed.

Therefore:

ES = max (EF of T3, EF of T4)

ES = max (8, 8) = 8

EF = 8 + 2 = 10

Therefore,

Project Duration = 10 weeks

Backward Pass Calculation

For T5:

LF = 10

LS = LF − Duration

LS = 10 − 2 = 8

For T3:

LF = 8

LS = 8 − 3 = 5

Therefore,

Latest Start Date of T3 = 5 weeks

For T4:

LF = 8

LS = 8 − 5 = 3

Earliest Start of T4 = 3 weeks.

Therefore:

Slack = LS − ES

Slack = 3 − 3 = 0 weeks

Therefore,

Slack Time of T4 = 0 weeks

PERT Calculation Table

| Task | Duration | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | 3 | 0 | 3 | 0 | 3 | 0 |
| T2 | 2 | 3 | 5 | 3 | 5 | 0 |
| T3 | 3 | 5 | 8 | 5 | 8 | 0 |
| T4 | 5 | 3 | 8 | 3 | 8 | 0 |
| T5 | 2 | 8 | 10 | 8 | 10 | 0 |

Critical Path

There are two critical paths:

- Path 1:

T1 → T2 → T3 → T5

Duration:

3 + 2 + 3 + 2 = 10 weeks

- Path 2:

T1 → T4 → T5

Duration:

3 + 5 + 2 = 10 weeks

Therefore,

Critical Paths = T1 → T2 → T3 → T5

and

T1 → T4 → T5

Results

- Project Duration = 10 weeks

- Latest Start Date of T3 = 5 weeks

- Slack Time of T4 = 0 weeks

- Critical Paths = T1 → T2 → T3 → T5 and T1 → T4 → T5

Conclusion

PERT is useful for analyzing and scheduling project activities. It helps determine the project duration, slack time and critical path. Activities with zero slack are critical activities, and a delay in these activities can delay the completion of the entire project.